## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Prince Kumar Yadav | 2026-01-08 | Missing values found in the user-item interaction dataset | milestone 1 | Prince Kumar Yadav | Logical | Cleaned dataset and handled missing values | 2026-01-05 | Closed | Dataset cleaned successfully
2 | Prince Kumar Yadav | 2026-01-08 | Incorrect column format in user-item matrix | milestone 1 | Prince Kumar Yadav | Logical | Corrected column structure and validated matrix format | 2026-01-06 | Closed | Matrix structure verified
3 | Prince Kumar Yadav | 2026-01-08 | dataset size was inconsistent after preprocessing | milestone 1 | Prince Kumar Yadav | Logical | Rechecked preprocessing logic and corrected dataset size | 2026-01-07 | Closed | Dataset finalized for model training
4 | Prince Kumar Yadav | 2026-01-09 |  | milestone2 | Prince Kumar Yadav

## Sheet2
Logical
User Interface
Maintainability
Standards
Others